## Test Plan Document
Test Plan Document
Scope | Test the functionality, usability, and performance of the BookHaven Online Bookstore web application.
Modules: Login, Book Search, Add-to-Cart, Cart, and Checkout.
Objectives | Ensure the application meets functional requirements.
Validate UI/UX for usability and accessibility.
Detect and log defects to improve quality.
Automate regression testing for core user flows.
Tools | Manual Testing: Google Sheets/Excel for test case documentation.
Automation Testing: Selenium with Python.
Bug Tracking: JIRA or Bugzilla.
UI/UX Testing: Accessibility tools (Lighthouse, Axe) and manual review.
Schedules
Activity | Start Date | End Date | Responsible Team
Test Plan Preparation | 2025-06-10 | 2025-06-11 | QA Team
Test Case Design | 2025-06-11 | 2025-06-16 | QA Team
Manual Testing Execution | 2025-06-11 | 2025-06-16 | QA Team
Automated Testing | 2025-06-13 | 2025-06-18 | Automation Team
Defect Reporting | 2025-06-13 | 2025-06-22 | QA Team

## Test Case Design
Test Case Design
Positive Test Cases
Test Case ID | Module | Test Steps | Expected Result
TC001 | Login | Enter your username and password, then click "Login" to access your account. | User is logged in and sees success message.
TC002 | Book Search | Type "Winnie-the-Pooh" in the search box to find the book. | "Winnie-the-Pooh" appears in results.
TC003 | Book Search | Type "Dr. Seuss" in the search box to find books by the author. | Books by Dr. Seuss are shown.
TC004 | Cart | Add a book to cart from book list. | Cart count increases by 1.
TC005 | Cart | View cart after adding book(s). | Cart displays added items correctly.
TC006 | Checkout | Checkout with items in cart. | Order success message is displayed.
TC011 | Navigation | Go to the menu and click on the "Browse Books" section. | Search/Browse section is visible.
TC012 | Book Search | Click "Show All" to display all books. | All books are listed in the results.
Negative Test Cases
Test Case ID | Module | Test Steps | Expected Result
TC007 | Login | Enter invalid credentials and click Login. | Error message: "Invalid email or password."
Boundary Test Cases
Test Case ID | Module | Test Steps | Expected Result
TC008 | Add-to-Cart | Add a book to cart up to its maximum stock. | Cannot exceed stock; alert shown if exceeded.
UI/UX Test Cases
Test Case ID | Module | Test Steps | Expected Result
TC009 | UI/UX | Check that all main buttons/links are labeled and accessible via keyboard. | All buttons are labeled and accessible.
TC010 | UI/UX | Check cart icon updates when items are added/removed. | Cart count updates correctly.

## Automation Test Coverage Table
Automation Test Coverage Table
Feature / Scenario | Selenium Test Method(s) | Test Case ID(s)
Valid Login | test_valid_login | TC001
Invalid Login | test_invalid_login | TC007
Search by Title | test_search_by_title | TC002
Search by Author | test_search_by_author | TC003
Navigation to Browse Books | test_navigation_to_search | TC011
Show All Books | test_show_all_books | TC012
Add to Cart | test_add_to_cart | TC004, TC008
Cart Display/Functionality | test_cart_functionality | TC005, TC010
Checkout Process | test_checkout_process | TC006

## UI & UX Testing Report
UI & UX Testing Report
Usability | All main sections can be accessed from the header menu.
The search bar is noticeable and easy to spot.
Accessibility | You can use the keyboard to navigate all buttons and links.
All form fields and interactive elements have clear labels.
Intuitiveness | Success and error messages are easy to understand and show up quickly.
Users get helpful instructions after logging in, adding items to the cart, and during checkout.
Issues Identified
Issue | Severity | Recommendation
No way to preview cart without full cart page | Low | Add dropdown on hover or icon click

## Defect Log
Defect Log
Defect ID | Module | Summary | Severity | Status
DEF-001 | Book Search | Search does not reset results | Low | Open
DEF-002 | Checkout | Cart not cleared after checkout | Medium | Open